## Task List
Week # | Task # | Task Description | Estimated Time (Hours) | Member Responsible | Complete? (Y/N) | Total Hours | 100.25
5 | 1 | Create the template task list. | 0.25 | Cleo | Y
5 | 2 | Plan the Task | 0.5 | Cleo | Y | Cleo | 100.25
5 | 3 | Approve the template task list. | 0.25 | Cleo | Y
5 | 4 | Init Literature Search | 5 | Cleo | Y
5 | 5 | Init Literature Review | 10 | Cleo | Y
5 | 6 | M1 Assignment Write up | 3 | Cleo | Y
5 | 7 | M1 Assignment proofreading and formatting | 1 | Cleo | Y
5 | 8 | M1 Assignment Submission | 0.25 | Cleo | Y
MILESTONE 1 DUE
6 | 1 | Design the Review Process | 3 | Cleo | N
6 | 2 | Literature Search - Current | 3 | Cleo | N
6 | 3 | Design the interview for idea collection | 3 | Cleo | N
6
6
7 | 1 | Literature Review - Current 1/3 | 5 | Cleo | N
7 | 2 | Summary and Analysis the Literatures | 3 | Cleo | N
7 | 3 | Literature Search - Future | 2 | Cleo | N
7
7
8 | 1 | Conduct the interview | 5 | Cleo | N
8 | 2 | Literature Review - Current 2/3 | 5 | Cleo | N
8
8
9 | 1 | Literature Review - Current 3/3 | 5 | Cleo | N
9 | 2 | Update the template task list. | 0.25 | Cleo | N
9 | 3 | Plan the remaining Tasks | 0.25 | Cleo | N
9 | 4 | Approve the template task list. | 0.25 | Cleo | N
9 | 5 | M2 Assignment Write up | 3 | Cleo | N
9 | 6 | M2 Assignment proofreading and formatting | 1 | Cleo | N
9 | 7 | M2 Assignment Submission | 0.25 | Cleo | N
MILESTONE 2 DUE
10 | 1 | Literature Review - Future 1/3 | 5 | Cleo | N
10 | 2 | Collect and organize data from Interviews | 1 | Cleo | N
10 | 3 | Analyzing and summarizing interview data | 3 | Cleo | N
10
10
11 | 1 | Literature Review - Future 2/3 | 5 | Cleo | N
11 | 2 | Literature Review - Future 3/3 | 5 | Cleo | N
11
11
12 | 1 | Summary and Analysis the Literatures | 5 | Cleo | N
12 | 2 | Plan the remaining Tasks | 0.25 | Cleo | N
12 | 3 | Approve the template task list. | 0.25 | Cleo | N
12 | 4 | M3 Assignment Write up | 3 | Cleo | N
12 | 5 | M3 Assignment proofreading and formatting | 1 | Cleo | N
12 | 6 | M3 Assignment Submission | 0.25 | Cleo | N
MILESTONE 3 DUE
13 | 1 | Summarize the findings to an academic paper | 5 | Cleo | N
13
13
13
13
14 | 1 | Come up with the poster | 3 | Cleo | N
14
14
14
14
15 | 1 | Prep transcripts for the presentation | 2 | Cleo | N
15 | 2 | Presentation Rehearsal | 1 | Cleo | N
15 | 3 | Record the Video Presentation | 1 | Cleo | N
15 | 4 | Term Project Submission | 0.25 | Cleo | N
FINAL REPORT (MILESTONE 4) DUE
Note on A1: The week of the semester, from week 5 to week 16.
Note on B1: An identifer for each task. This is just used for easier conversation, e.g. "It looks like you didn't finish Task 5."
Note on C1: A brief (~1 sentence or fragment) description of the task.
Note on D1: The estimated number of hours to complete the task.
Note on E1: For team projects, which team member is responsible for the task.
Note on H3: Your name can be placed here to auto-sum your hours.